## Sheet1
LIFE Mission - Physical Progress Report of Phase-2(SC - As on 21.01.2020)
Sl No | DISTRICT | Approved Beneficiaries | Eligible Benificiaries | Agreement executed | Physical Progress - Stages of Completion | [5 empty] | % of Completion
[5 empty] | Not started | Started | Basement | Lintel | Roof | Completed
1 | THIRUVANATHAPURAM | 3431 | 1740 | 1058 | 24 | 0 | 80 | 161 | 209 | 584 | 55.2%
2 | KOLLAM | 2898 | 1484 | 1312 | 72 | 0 | 112 | 119 | 140 | 869 | 66.23%
3 | PATHANAMTHITTA | 775 | 321 | 260 | 5 | 0 | 9 | 30 | 50 | 166 | 63.85%
4 | ALAPUZHA | 1512 | 847 | 678 | 61 | 20 | 56 | 61 | 131 | 349 | 51.47%
5 | KOTTAYAM | 773 | 465 | 391 | 23 | 8 | 31 | 32 | 54 | 243 | 62.15%
6 | IDUKKI | 2955 | 2067 | 1691 | 125 | 66 | 212 | 373 | 244 | 671 | 39.68%
7 | ERNAKULAM | 1182 | 576 | 576 | 10 | 20 | 10 | 34 | 72 | 430 | 74.65%
8 | THRISSUR | 1695 | 763 | 599 | 10 | 0 | 30 | 28 | 116 | 415 | 69.28%
9 | PALAKKAD | 2589 | 1299 | 952 | 83 | 0 | 72 | 111 | 173 | 513 | 53.89%
10 | MALAPPURAM | 1262 | 635 | 522 | 5 | 67 | 18 | 22 | 60 | 350 | 67.05%
11 | KOZHIKODU | 1078 | 420 | 403 | 6 | 1 | 28 | 54 | 61 | 253 | 62.78%
12 | WAYANAD | 498 | 193 | 193 | 23 | 0 | 15 | 21 | 56 | 78 | 40.41%
13 | KANNUR | 133 | 59 | 59 | 3 | 0 | 6 | 8 | 10 | 32 | 54.24%
14 | KASARAGOD | 271 | 97 | 70 | 1 | 0 | 5 | 4 | 15 | 45 | 64.29%
TOTAL |  | 21052 | 10966 | 8764 | 451 | 182 | 684 | 1058 | 1391 | 4998 | 57.03%