## Sheet1
LIFE Mission - Physical Progress Report of Phase-2(ST - As on 21.01.2020)
Sl No | DISTRICT | Approved Beneficiaries | Eligible Benificiaries | Agreement executed | Physical Progress - Stages of Completion | [5 empty] | % of Completion
[5 empty] | Not started | Started | Basement | Lintel | Roof | Completed
1 | THIRUVANATHAPURAM | 1013 | 443 | 165 | 9 | 0 | 20 | 26 | 15 | 95 | 57.58%
2 | KOLLAM | 139 | 25 | 20 | 1 | 0 | 2 | 1 | 7 | 9 | 45%
3 | PATHANAMTHITTA | 78 | 18 | 18 | 0 | 0 | 0 | 4 | 5 | 9 | 50%
4 | ALAPUZHA | 34 | 14 | 8 | 0 | 0 | 0 | 2 | 4 | 2 | 25%
5 | KOTTAYAM | 97 | 69 | 57 | 1 | 3 | 4 | 3 | 4 | 42 | 73.68%
6 | IDUKKI | 1501 | 1161 | 1046 | 164 | 94 | 241 | 268 | 108 | 171 | 16.35%
7 | ERNAKULAM | 166 | 113 | 113 | 4 | 15 | 18 | 20 | 22 | 34 | 30.09%
8 | THRISSUR | 46 | 31 | 32 | 6 | 0 | 0 | 8 | 6 | 12 | 37.5%
9 | PALAKKAD | 214 | 134 | 96 | 13 | 0 | 6 | 12 | 38 | 27 | 28.12%
10 | MALAPPURAM | 53 | 45 | 43 | 8 | 2 | 7 | 5 | 10 | 11 | 25.58%
11 | KOZHIKODU | 66 | 33 | 32 | 0 | 0 | 7 | 8 | 8 | 9 | 28.12%
12 | WAYANAD | 921 | 505 | 505 | 25 | 0 | 47 | 75 | 221 | 137 | 27.13%
13 | KANNUR | 170 | 110 | 110 | 4 | 15 | 5 | 20 | 16 | 50 | 45.45%
14 | KASARKODU | 1133 | 798 | 761 | 6 | 0 | 67 | 42 | 240 | 406 | 53.35%
TOTAL |  | 5631 | 3499 | 3006 | 241 | 129 | 424 | 494 | 704 | 1014 | 33.73%